## Task View
Scrum Time 1.0 Tasks
Alizarin
story list
Create story table
Create story domain object
Story list view
Story list controller method
CSS or javascript for hover, etc.
new story
Partial edit story view
Partial edit story controller method
CSS or javascript for hover, etc.
Save controller method
Cancel controller method
Handle priority change
delete story
Partial delete story view
Partial delete controller method
CSS or javascript for hover, etc.
Yes controller method
No controller method
Edit story
Click from list view to controller edit method
CSS or javascript for hover, etc.
List tasks
Create task table
Create task domain object
Task list view
Task list controller method
CSS or javascript for hover, etc.
Close tasks controller method in story controller
New task
Partial edit task view
Partial edit task controller method
CSS or javascript for hover, etc.
Save controller method
Cancel controller method
Handle priority change
Delete task
Partial delete task view
Partial delete controller method
CSS or javascript for hover, etc.
Yes controller method
No controller method
Edit task
Click from list view to controller edit method
CSS or javascript for hover, etc.

## Story View
Stories
Priority | Id | Narrative | Points
1 | story list | As a product owner, I want to be able to see the list of all stories associated with the product. | 40
2 | my assigned tasks | As a scrum team member, I want to see all of the tasks that are assigned to me. | 13
2 | assign tasks | As a scrum master, I want to assign tasks to my team members. | 13
3 | story ids | As a product owner, I want the stories to have id's that may be numbers and/or characters so that they may be named or even split into different phases. | 13
3 | story spreadsheet | As a product owner, I want the stories to be entered as if creating a spreadsheet | 40
4 | narrative optional | As a product owner, I do not care if there is a narrative for a story as long as there is an id for the story. | 3
5 | priority collisions | As a product owner, I want the system to handle the scenario of a user selecting a priority that already exists. | 8
6 | release/sprint builder | As a product owner, I want to be able to highlight discontinuous sets of stories and select them for completion in a release or sprint. | 40
7 | new story | As a product owner, I want to be able to create a new story. | 13
8 | delete story | As a product owner, I want to be able to delete a new story.
12 | copy narrative | As a product owner, I want to be able to easily copy a story narrative and paste it into an new or editable story. | 13
20 | sortable backlog | As a product owner, I want the columns of the story backlog to be sortable for any column. | 40
21 | n-level story grouping | As a product owner, I want to be able to group stories to n-levels | 100
30 | filter story list | As a product owner, I want to be able to filter the list of stories that are visible. | 40
50 | restrict story columns | As a product owner, I want to be able to restrict the visible columns in the story backlog. | 40
40 | toggle all tasks | As a product owner, I want to be able to toggle the display of all tasks at one time for all stories within the displayed story backlog. | 100
50 | attach artifacts | As a product owner, I want to be able to attach files/artifacts to the stories or to the tasks. | 100
30 | self-contained installer | As a first time user, I want the installer to be fully self-contained such that I do not need to have IIS installed. | 40